## Timeline Instructions
2024 Give Back Project Timeline Template
All Leadership Academy Fellows will plan, manage, and execute a Give Back Project allowing you to take what you have learned through classes and Leadership Academy and pass that knowledge along to your communities. The products you build can take various forms that leverage your technical skills and goals. By the end of the program, you will have your product in a beta testing stage.
Template Instructions
Need a review of what the Give Back Project is and the timeline for this program? Click Here!
Step 1: Task Breakdown
To get started, list out all the tasks you can think of that are associated with your project. This list should include a long number of specific tasks that must get done to ensure you meet each Milestone deadline.
Step 2: Milestons
Now that you've listed all your tasks, copy them over to the Task List column and categorize them tasks under each milestone. Check and see if anything is missing!
Step 3: Assign
Copy the tasks and Milestones over. Now assign a due date to teach task and who should complete the task. Optionally, it's helpful to include how long you think the task will take to complete.
Step 4: Final Timeline
The final step outlines key deliverables, timelines, and milestones across August to November. Users should list detailed tasks under each milestone, assign owners and durations, highlight any important cells, and regularly update progress in the corresponding weekly columns to ensure timely completion. Adjustments can be made as necessary to maintain alignment with deadlines and overall project goals, culminating in the final presentation and program survey by December 2nd.

## Step 1 Task Breakdown
Step 1: Task Breakdown
To get started, list out all the tasks you can think of that are associated with your project. This list should include a long number of specific tasks that must get done to ensure you meet each Milestone deadline.
As a reminder, your milestones include a Research & Outline, Minimal Viable Product, Final Product, and a Presentation.
Task Number | Task (Name and/or Description) | Notes
Task 1 | Choose programming language | Milestone 2
Task 2 | Decide what needs to be learned before beginning the project (Machine Learning, Model Evanluation methods, Website Development, Design) | Milestone 2
Task 3 | Find best datasets for diabetes and ethnicity data. | Milestone 2
Task 4 | Research different machine learning models/algorithms | Milestone 2
Task 5 | Research available tools, libraries, and frameworks for model development | Milestone 2
Task 6 | Identify best evaluation metric | Milestone 2
Task 7 | Create documentation page for the sources and research. | Milestone 2
Task 8 | Data Collection: Gather data/complie a dataset | Milestone 3 (MVP)
Task 9 | Data Preprocessing: Clean and preprocess dataset such as removing outliers, handling missing data, etc. | Milestone 3 (MVP)
Task 10 | Exploratory Data Analysis (EDA): explore data and perform data analysis | Milestone 3 (MVP)
Task 11 | Feature engineering: create features based on data and normalize | Milestone 3 (MVP)
Task 12 | Split the Dataset (training, validation, and test sets) | Milestone 3 (MVP)
Task 13 | Generate descriptive statistics for the dataset | Milestone 3 (MVP)
Task 14 | Create data visualizations to see feature distribution | Milestone 3 (MVP)
Task 15 | Identify patterns within the data | Milestone 3 (MVP)
Task 16 | Select Algorithm for predicting diabetes risk | Milestone 3 (MVP)
Task 17 | Train the Model | Milestone 3 (MVP)
Task 18 | Validate the Model: evaluate the model's performance using accuracy, precision, F1 score, etc. | Milestone 3 (MVP)
Task 19 | Fine tune the model: improve performance by adjusting hyperparameters | Milestone 3 (MVP)
Task 20 | Cross-validate model and ensure it is not overfitting or underfitting | Milestone 3 (MVP)
Task 21 | Create a simiple UI for users to input their health information and receive their risk prediction | Milestone 3 (MVP)
Task 22 | Integrate the ML model with the UI so user inputs are put into the model for prediciton. | Milestone 3 (MVP)
Task 23 | Frontend implementation: Create dropdowns for users to input health info | Milestone 3 (MVP)
Task 24 | Create a results display section for users to see their risk score. | Milestone 3 (MVP)
Task 25 | Test model with 'user data' to make sure predictions are accurate and consistent | Milestone 3 (MVP)
Task 26 | Test the simple UI | Milestone 3 (MVP)
Task 27 | Implement error handling for user inputs | Milestone 3 (MVP)
Task 28 | Create interactive visualizations | Milestone 4 (Addition and Nice to have features)
Task 29 | Implement interactive visualizations to the UI | Milestone 4 (Addition and Nice to have features)
Task 30 | Develop a recommendation algorithm for personalized health recommendations based on risk score | Milestone 4 (Addition and Nice to have features)
Task 31 | Add a tab for a section with general advice for diabetes prevention | Milestone 4 (Addition and Nice to have features)
Task 32 | Connect risk prediction model with recommendation algorithm so users receive both right away | Milestone 4 (Addition and Nice to have features)
Task 33 | Testing interactive visuals, website, recommendation, and risk prediction | Milestone 5
Task 34 | Create a demo of website use: show visuals, the risk prediction, and recommendations | Milestone 5
Task 35 | Create presentation slides to show: problem, solution, machine learning model, findings, video demo, results, how our site can help users | Milestone 5
Task 36 | Assign speaking roles to team members | Milestone 5
Task 37 | Add demo video to presentation slides | Milestone 5
Task 38 | Practice video presentation | Milestone 5
Task 39 | Create presentation video | Milestone 5
Task 40
Task 41
Task 42
Task 43
Task 44
Task 45
Task 46
Task 47
Task 48
Task 49
Task 50
Task 51
Task 52
Task 53
Task 54
Task 55
Task 56
Task 57
Task 58
Task 59
Task 60
Task 61
Task 62
Task 63
Task 64

## Step 2 Milestones
Now that you've listed all your tasks, copy them over to the Task List column and categorize them tasks under each milestone. Check and see if anything is missing!
Task (Name and/or Description) | Milestone: | Notes
Choose programming language | Milestone #2 - Research and Product Outline
Decide what needs to be learned before beginning the project (Machine Learning, Model Evanluation methods, Website Development, Design) | Milestone #2 - Research and Product Outline
Find best datasets for diabetes and ethnicity data. | Milestone #2 - Research and Product Outline
Research different machine learning models/algorithms | Milestone #2 - Research and Product Outline
Research available tools, libraries, and frameworks for model development | Milestone #2 - Research and Product Outline
Identify best evaluation metric | Milestone #2 - Research and Product Outline
Create documentation page for the sources and research. | Milestone #2 - Research and Product Outline
Milestone #2: Submit Research and Product Outline | Milestone #2 - Research and Product Outline
Data Collection: Gather data/complie a dataset | Milestone #3 - Product MVP
Data Preprocessing: Clean and preprocess dataset such as removing outliers, handling missing data, etc. | Milestone #3 - Product MVP
Exploratory Data Analysis (EDA): explore data and perform data analysis | Milestone #3 - Product MVP
Feature engineering: create features based on data and normalize | Milestone #3 - Product MVP
Split the Dataset (training, validation, and test sets) | Milestone #3 - Product MVP
Generate descriptive statistics for the dataset | Milestone #3 - Product MVP
Create data visualizations to see feature distribution | Milestone #3 - Product MVP
Identify patterns within the data | Milestone #3 - Product MVP
Select Algorithm for predicting diabetes risk | Milestone #3 - Product MVP
Milestone #2.5: Timeline Resubmission | Milestone #3 - Product MVP
Train the Model | Milestone #3 - Product MVP
Validate the Model: evaluate the model's performance using accuracy, precision, F1 score, etc. | Milestone #3 - Product MVP
Fine tune the model: improve performance by adjusting hyperparameters | Milestone #3 - Product MVP
Cross-validate model and ensure it is not overfitting or underfitting | Milestone #3 - Product MVP
Create a simiple UI for users to input their health information and receive their risk prediction | Milestone #3 - Product MVP
Integrate the ML model with the UI so user inputs are put into the model for prediciton. | Milestone #3 - Product MVP
Frontend implementation: Create dropdowns for users to input health info | Milestone #3 - Product MVP
Create a results display section for users to see their risk score. | Milestone #3 - Product MVP
Test model with 'user data' to make sure predictions are accurate and consistent | Milestone #3 - Product MVP
Test the simple UI | Milestone #3 - Product MVP
Implement error handling for user inputs | Milestone #3 - Product MVP
Milestone #3: Submit Product MVP | Milestone #3 - Product MVP
Create interactive visualizations | Milestone #4 - Product "Nice to Haves"
Implement interactive visualizations to the UI | Milestone #4 - Product "Nice to Haves"
Develop a recommendation algorithm for personalized health recommendations based on risk score | Milestone #4 - Product "Nice to Haves"
Add a tab for a section with general advice for diabetes prevention | Milestone #4 - Product "Nice to Haves"
Connect risk prediction model with recommendation algorithm so users receive both right away | Milestone #4 - Product "Nice to Haves"
Milestone #4: Submit Product 'Nice to Haves' | Milestone #4 - Product "Nice to Haves"
Testing interactive visuals, website, recommendation, and risk prediction | Milestone #5 - Presentation and Testing
Create a demo of website use: show visuals, the risk prediction, and recommendations | Milestone #5 - Presentation and Testing
Create presentation slides to show: problem, solution, machine learning model, findings, video demo, results, how our site can help users | Milestone #5 - Presentation and Testing
Assign speaking roles to team members | Milestone #5 - Presentation and Testing
Add demo video to presentation slides | Milestone #5 - Presentation and Testing
Practice video presentation | Milestone #5 - Presentation and Testing
Create presentation video | Milestone #5 - Presentation and Testing
Milestone #5: Submit Presentation and Testing on Forage | Milestone #5 - Presentation and Testing

## Step 3 Assign
Step 3: Assign
Copy the tasks and Milestones over. Now assign a due date to teach task and who should complete the task. Optionally, it's helpful to include how long you think the task will take to complete.
Task (Name and/or Description) | Milestone: | Due Date: | Owner: | Notes:
Choose programming language | Milestone #2 - Research and Product Outline | 2024-09-16 | Lizbeth | Duration: Less than a day
Decide what needs to be learned before beginning the project (Machine Learning, Model Evanluation methods, Website Development, Design) | Milestone #2 - Research and Product Outline | 2024-09-18 | Patricia | Duration: 1 day
Find best datasets for diabetes and ethnicity data. | Milestone #2 - Research and Product Outline | 2024-09-18 | Patricia | Duration: 1 day
Research different machine learning models/algorithms | Milestone #2 - Research and Product Outline | 2024-09-20 | Patricia | Duration: 2 days and let Kaitly know your findings
Research available tools, libraries, and frameworks for model development | Milestone #2 - Research and Product Outline | 2024-09-20 | Kaitly | Duration: 1 day
Identify best evaluation metric | Milestone #2 - Research and Product Outline | 2024-09-21 | Kaitly | Duration: Less than a day
Create documentation page for the sources and research. | Milestone #2 - Research and Product Outline | 2024-09-22 | Patricia | Duration: 1 day
Milestone #2: Submit Research and Product Outline | Milestone #2 - Research and Product Outline | 2024-09-23 | All | Duration: A couple of hours to finalize
Data Collection: Gather data/complie a dataset | Milestone #3 - Product MVP | 2024-10-02 | Patricia | Duration: 3 days and let other teammates know early on if you are having issues completing this task.
Data Preprocessing: Clean and preprocess dataset such as removing outliers, handling missing data, etc. | Milestone #3 - Product MVP | 2024-10-05 | Patricia and Lizbeth | Duration: 2 days and let others know early on if you are having trouble completing this task.
Exploratory Data Analysis (EDA): explore data and perform data analysis | Milestone #3 - Product MVP | 2024-10-10 | Lizbeth | Duration: 2 days
Feature engineering: create features based on data and normalize | Milestone #3 - Product MVP | 2024-10-12 | Kaitly and Lizbeth | Duration: 2 days
Split the Dataset (training, validation, and test sets) | Milestone #3 - Product MVP | 2024-10-14 | Kaitly | Duration: Less than a day
Generate descriptive statistics for the dataset | Milestone #3 - Product MVP | 2024-10-15 | Lizbeth | Duration: 1 day
Create data visualizations to see feature distribution | Milestone #3 - Product MVP | 2024-10-17 | Lizbeth | Duration: 1.5 days
Identify patterns within the data | Milestone #3 - Product MVP | 2024-10-18 | Lizbeth | Duration: 1 day
Select Algorithm for predicting diabetes risk | Milestone #3 - Product MVP | 2024-10-20 | Kaitly | Duration: 1 day
Milestone #2.5: Timeline Resubmission | Milestone #3 - Product MVP | 2024-10-21 | All | Duration: A couple of hours to finalize
Train the Model | Milestone #3 - Product MVP | 2024-10-22 | Kaitly | Duration: 2 days
Validate the Model: evaluate the model's performance using accuracy, precision, F1 score, etc. | Milestone #3 - Product MVP | 2024-10-24 | Kaitly and Lizbeth | Duration: 2 days
Fine tune the model: improve performance by adjusting hyperparameters | Milestone #3 - Product MVP | 2024-10-26 | Kaitly and Lizbeth | Duration: 2 days
Cross-validate model and ensure it is not overfitting or underfitting | Milestone #3 - Product MVP | 2024-10-27 | Kaitly and Lizbeth | Duration: 1.5 days
Create a simiple UI for users to input their health information and receive their risk prediction | Milestone #3 - Product MVP | 2024-10-24 | Suraya | Duration: 3 days
Integrate the ML model with the UI so user inputs are put into the model for prediciton. | Milestone #3 - Product MVP | 2024-10-26 | Suraya and Kaitly | Duration: 2 days
Frontend implementation: Create dropdowns for users to input health info | Milestone #3 - Product MVP | 2024-10-27 | Suraya | Duration: 1 day
Create a results display section for users to see their risk score. | Milestone #3 - Product MVP | 2024-10-27 | Suraya | Duration: 1 day
Test model with 'user data' to make sure predictions are accurate and consistent | Milestone #3 - Product MVP | 2024-10-27 | Suraya and Kaitly | Duration: 1 day
Test the simple UI | Milestone #3 - Product MVP | 2024-10-28 | Suraya and Patricia | Duration: 1 day
Implement error handling for user inputs | Milestone #3 - Product MVP | 2024-10-28 | Suraya | Duration: 1 day
Milestone #3: Submit Product MVP | Milestone #3 - Product MVP | 2024-10-28 | All | Duration: A couple of hours to finalize
Create interactive visualizations | Milestone #4 - Product "Nice to Haves" | 2024-11-04 | Lizbeth | Duration: 3 days
Implement interactive visualizations to the UI | Milestone #4 - Product "Nice to Haves" | 2024-11-07 | Lizbeth | Duration: 2 days
Develop a recommendation algorithm for personalized health recommendations based on risk score | Milestone #4 - Product "Nice to Haves" | 2024-11-04 | Kaitly and Patricia | Duration: 3 days
Add a tab for a section with general advice for diabetes prevention | Milestone #4 - Product "Nice to Haves" | 2024-11-07 | Patricia | Duration: 1 day
Connect risk prediction model with recommendation algorithm so users receive both right away | Milestone #4 - Product "Nice to Haves" | 2024-11-10 | Kaitly and Suraya | Duration: 2 days
Milestone #4: Submit Product 'Nice to Haves' | Milestone #4 - Product "Nice to Haves" | 2024-11-11 | All | Duration: A couple of hours to finalize
Testing interactive visuals, website, recommendation, and risk prediction | Milestone #5 - Presentation and Testing | 2024-11-14 | Patrica | Duration: 2 days
Create a demo of website use: show visuals, the risk prediction, and recommendations | Milestone #5 - Presentation and Testing | 2024-11-16 | Suraya and Patricia | Duration: 2 days
Create presentation slides to show: problem, solution, machine learning model, findings, video demo, results, how our site can help users | Milestone #5 - Presentation and Testing | 2024-11-16 | All | Duration: 2 days
Assign speaking roles to team members | Milestone #5 - Presentation and Testing | 2024-11-16 | Patricia | Duration: less than a day
Add demo video to presentation slides | Milestone #5 - Presentation and Testing | 2024-11-16 | Patricia | Duration: less than a day
Practice video presentation | Milestone #5 - Presentation and Testing | 2024-11-17 | All | Duration: 1 day
Create presentation video | Milestone #5 - Presentation and Testing | 2024-11-17 | All | Duration: 1 day
Milestone #5: Submit Presentation and Testing on Forage | Milestone #5 - Presentation and Testing | 2024-11-18 | All | Duration: A couple of hours to finalize

## Step 4 Final Timeline
PROJECT NAME: Operation: Diabetes Prevention LEADERSHIP ACADEMY FELLOWS: Lizbeth, Kaitly, Patricia, Allison, Suraya |  |  |  | August |  |  | September |  |  |  |  | October |  |  |  | November
Deliverables | Owner (who will complete the deliverable) | Duration (# of weeks) | Deadline | 8/13 - 8/18 | 8/19 - 8/25 | 8/26 - 9/1 | 9/2 - 9/8 | 9/9 - 9/15 | 9/16 - 9/22 | 9/23 - 9/29 | 9/30 - 10/6 | 10/7 - 10/13 | 10/14 - 10/20 | 10/21 - 10/27 | 10/28 - 11/3 | 11/4 - 11/10 | 11/11 - 11/17 | 11/18 - 11/24 | 11/24 - 12/2
Key Program Dates
Planning/Proposal Phase |  | 3 wks
Review Handbook and Give Back Project Resources |  | 1 wk
Milestone 1: Project and Milestone Proposal Due |  | 2 wk | 2024-09-03
Milestone 1.5: Timeline Due |  | 1 wk | 2024-09-16
Milestone 2: Research and Product Outline |  | 2 wks
Choose programming language | Lizbeth | Duration: Less than a day | 2024-09-16
Decide what needs to be learned | Patricia | Duration: 1 day | 2024-09-18
Find best datasets for diabetes/ethnicity data. | Patricia | Duration: 1 day | 2024-09-18
Research different machine learning models/algorithms | Patricia | Duration: 2 days | 2024-09-20
Research available tools, libraries, and frameworks for model development | Kaitly | Duration: 1 day | 2024-09-20
Identify best evaluation metric | Kaitly | Duration: Less than a day | 2024-09-21
Create documentation page for the sources and research. | Patricia | Duration: 1 day | 2024-09-22
Milestone #2: Submit Research and Product Outline | All | Duration: A couple of hours | 2024-09-23
Milestone 2: Research and Product Outline Due |  |  | 2024-09-23
[Optional] Timeline Resubmission Due |  | 1 wk | 2024-10-21
Project Execution |  | 8 wks
Data Collection: Gather data/complie a dataset | Patricia | Duration: 3 days | 2024-10-02
Data Preprocessing: Clean and preprocess dataset such as removing outliers, handling missing data, etc. | Patricia and Lizbeth | Duration: 2 days | 2024-10-05
Exploratory Data Analysis (EDA): explore data and perform data analysis | Lizbeth | Duration: 2 days | 2024-10-10
Feature engineering: create features based on data and normalize | Kaitly and Lizbeth | Duration: 2 days | 2024-10-12
Split the Dataset (training, validation, and test sets) | Kaitly | Duration: Less than a day | 2024-10-14
Generate descriptive statistics for the dataset | Lizbeth | Duration: 1 day | 2024-10-15
Create data visualizations to see feature distribution | Lizbeth | Duration: 1.5 days | 2024-10-17
Identify patterns within the data | Lizbeth | Duration: 1 day | 2024-10-18
Select Algorithm for predicting diabetes risk | Kaitly | Duration: 1 day | 2024-10-20
Milestone #2.5: Timeline Resubmission | All | Duration: A couple of hours | 2024-10-21
Train the Model | Kaitly | Duration: 2 days | 2024-10-22
Validate the Model: evaluate the model's performance using accuracy, precision, F1 score, etc. | Kaitly and Lizbeth | Duration: 2 days | 2024-10-24
Fine tune the model: improve performance by adjusting hyperparameters | Kaitly and Lizbeth | Duration: 2 days | 2024-10-26
Cross-validate model and ensure it is not overfitting or underfitting | Kaitly and Lizbeth | Duration: 1.5 days | 2024-10-27
Create a simiple UI for users to input their health information and receive their risk prediction | Suraya | Duration: 3 days | 2024-10-24
Integrate the ML model with the UI so user inputs are put into the model for prediciton. | Suraya and Kaitly | Duration: 2 days | 2024-10-26
Frontend implementation: Create dropdowns for users to input health info | Suraya | Duration: 1 day | 2024-10-27
Create a results display section for users to see their risk score. | Suraya | Duration: 1 day | 2024-10-27
Test model with 'user data' to make sure predictions are accurate and consistent | Suraya and Kaitly | Duration: 1 day | 2024-10-27
Test the simple UI | Suraya and Patricia | Duration: 1 day | 2024-10-28
Implement error handling for user inputs | Suraya | Duration: 1 day | 2024-10-28
Milestone #3: Submit Product MVP | All | Duration: A couple of hours | 2024-10-28
Milestone 3: MVP (Minimum Viable Product) complete |  |  | 2024-10-28
Create interactive visualizations | Lizbeth | Duration: 3 days | 2024-11-04
Implement interactive visualizations to the UI | Lizbeth | Duration: 2 days | 2024-11-07
Develop a recommendation algorithm for personalized health recommendations based on risk score | Kaitly and Patricia | Duration: 3 days | 2024-11-04
Add a tab for a section with general advice for diabetes prevention | Patricia | Duration: 1 day | 2024-11-07
Connect risk prediction model with recommendation algorithm so users receive both right away | Kaitly and Suraya | Duration: 2 days | 2024-11-10
Milestone #4: Submit Product 'Nice to Haves' | All | Duration: A couple of hours | 2024-11-11
Milestone 4: Final Product Build |  |  | 2024-11-11
Final Presentation |  | 2 wks
Testing interactive visuals, website, recommendation, and risk prediction | Patrica | Duration: 2 days | 2024-11-14
Create a demo of website use: show visuals, the risk prediction, and recommendations | Suraya and Patricia | Duration: 2 days | 2024-11-16
Create presentation slides to show: problem, solution, machine learning model, findings, video demo, results, how our site can help users | All | Duration: 2 days | 2024-11-16
Assign speaking roles to team members | Patricia | Duration: less than a day | 2024-11-16
Add demo video to presentation slides | Patricia | Duration: less than a day | 2024-11-16
Practice video presentation | All | Duration: 1 day | 2024-11-17
Create presentation video | All | Duration: 1 day | 2024-11-17
Milestone #5: Submit Presentation and Testing on Forage | All | Duration: A couple of hours | 2024-11-18
Milestone 5: Presentation |  |  | 2024-11-18
End of Program Survey |  |  | 2024-12-02